## Sheet1
# | Item | Code (LOC, est.) | Tests (LOC, est.) | Basis for estimate
1 | OSC-8 hyperlinks | 40–60 | 80–120 + 2–3 golden fixtures | Small addition to Terminal.hs capability detection (like existing capNoColor/capForceColor) + conditional wrap in Graphical.hs. Test ratio follows TermColor.hs (2.3× code).
2 | Same-line multi-label packing | 150–250 | 150–220 + 4–6 golden fixtures | This is a new lane-assignment engine on the horizontal axis, not an extension of Layout.hs — your own PENDING_WORK.md says so. Sized similarly to Layout.hs+LinePlan.hs combined (160 LOC) since it's comparable proof complexity, plus wiring into Graphical.hs.
3 | Collection labels in derive macro | 60–100 | 60–100 + 2–4 compile-fail fixtures | Context.hs already supports variable-length label lists — this is TH-layer only (new DiagnosticSpec field option, reify validation, dispatch through existing buildContextWith). Smaller than the base derive macro since it reuses existing plumbing.
4 | Lazy/file-backed SourceCode | 250–400 | 150–250 | Largest item: new module for windowed file/mmap reads, plus Context/Span/Render need to become backend-polymorphic instead of hardcoding NamedSource. Touches ~5 modules, not just one.
5 | Width-aware wrapping | 90–140 | 70–100 + 2–3 golden fixtures | New Config field/setter (~15 LOC) + reflow logic in Graphical.hs/Narratable.hs keeping gutter alignment.
6 | Syntax highlighting | 200–350 | 150–200 + several fixtures | Needs a new module wrapping an external Haskell highlighter, merging its output with existing label-color ANSI styling without clobbering carets. Heaviest dependency-integration item, as your own docs flag.
| Total | ~790–1300 | ~660–1000